## Sheet1
About: We're looking for problems with the documentation that need work. Out of date, incorrect, missing, old name, needs to move, needs versioning. This is a quick Punchlist.
Summary / Name | Due Diligence Person | Create/Keep/Trash/Update? | Status | Owner | Targeted Persona | Description | Original URL / Reference | Updated Version
Documentation home page branding |  | In progress |  | James | All | Link to Docs from the tungsten.io menu goes to a github.io site that looks and feels different than tungsten.io. Update: fixed this, but needs improvement in mobile browsers (e.g. hamburger icon in the header menu). Also we should move the main page to an index.md file and use the readme.md properly as a guide for those coming to the code in the repo. | https://tungstenfabric.github.io/website/
Documentation home doesn't break out to all docs use cases |  |  |  |  | All | A documentation home page should link out to all the use cases that something could want to use the docs such as reference of APIs, reference of concepts, features, getting started sandboxes, getting started as a developer, etc. | https://tungstenfabric.github.io/website/
Getting started in 10 mintues needs updating |  |  |  |  | All | Rename: "10 Minute Tungsten Fabric Quick Start!" | https://github.com/tungstenfabric/website/wiki/Tungsten-Fabric:-10-minute-deployment-with-k8s-on-AWS
Becoming a contributor broken link |  |  |  |  | Contributing Developers | In the third item of this list, when clicking on "Create a Launchpad account", it sends me to a broken link where all I get is "Invalid OpenID transaction" error. | https://tungstenfabric.github.io/website/
Include Helm deployment documentation | [5 empty] | In the "Start using Tungsten Fabric" section, we could include documentation for a Helm-based deployment. | https://tungstenfabric.github.io/website/
TF101 Deck |  | Create | v1.0 | Randy | Newbies |  | https://drive.google.com/open?id=1gtZeM1IhL0krEr9XMIkcPQL_k480Nhpl
TF201 "Deep Dive" Deck |  | Create | MVP | Randy | Intermediates |  | https://docs.google.com/presentation/d/1E1cS0qPFX1YPgzXXx4CYH_mysc74G4l3HAI4MIUbMXE/edit?usp=sharing
TF Contributor Deck |  | Create | MVP | Randy | New contributors |  | https://docs.google.com/presentation/d/1R6vaVNqC9j5OfmKyKvcSfOX71iGoG3yxfUcJRMDQnvI/edit?usp=sharing
RANDY'S NOTES BELOW
OC: Getting Started vs. Quick Start Guide | Greg |  |  |  | All | Are these the same thing on the old OpenContrail.org site? Getting started page references quick start guide | http://www.opencontrail.org/deploying-opencontrail/
Do we need a build guide? | N/A |  |  |  | Contributing Developers, Packagers, & Distributors | We have a contributor getting started, which should be expanded to include this information | https://github.com/tungstenfabric/docs/blob/master/Contributor/GettingStarted/getting-started-with-opencontrail-development.md
OC: Deploying OpenContrail | Greg |  |  |  | ? | Delete or roll into a build guide | http://github.com/Juniper/contrail-controller and http://github.com/Juniper/contrail-vrouter
OC: Network Virtualization Architecture Deep Dive | Greg |  |  |  | All | Is this still relevant? Is it up to date? | http://www.opencontrail.org/network-virtualization-architecture-deep-dive/
OC: Architecture overview | Greg | Update | v1.0 |  | Contributing Developers | This seems like a simple "architectural overview" that would ideally more front and center in terms of explaining to new contributors how the whole thing is wired together - probably needs an update | http://juniper.github.io/contrail-vnc/architecture.html
OC: OpenContrail Architecture Document | Stuart Mackie |  |  |  | TBD | Probably needs an update; seems to overlap with eBook amongst other things | http://www.opencontrail.org/opencontrail-architecture-documentation/ | https://docs.google.com/document/d/12pQscvJ1roftoQfV9XK4Akxe5tXTlyGKah3P-ozhnmQ/edit?usp=sharing
OC: OpenContrail Architecture ("Day One") eBook | Greg |  |  |  | TBD | Update to TF; contact Ankur about doing the work on his behalf | http://www.opencontrail.org/ebook/
Document graph/workflow | Randy |  |  |  | All | Which docs for which personas at which times? | TBD
OC: API documentation (all) | Greg |  |  |  | All | Rebase to Tungsten.io ; still need to rebrand ; move to readthedocs? | N/A
OC: Installation guide | Randy |  |  |  | TBD | For Contrail 1.06?? Seems out of date but also potentially overlapping with getting started, quick start guide, deploying, and various others | https://github.com/Juniper/contrail-controller/wiki/Install-and-Configure-OpenContrail-1.06
Personas we care about | N/A |  |  |  | N/A | Contributing developers (write code for TF), application developers (building their own apps on k8s+TF), network operators/engineers/architects
New TF CI infrastructure documentation | Randy |  |  |  | Contributing Developers | TBD | https://github.com/Juniper/contrail-infra-doc
CC: Feature Guide | Randy |  |  | JNPR TechPubs |  |  | TBD (will be committed to contrail-dcos) shortly
CC: Getting Started Guide | Randy |  |  | JNPR TechPubs |  | Truncated CC: Feature Guide | TBD (will be committed to contrail-dcos) shortly
CC: Release Notes | Randy |  |  | JNPR TechPubs |  |  | https://github.com/Juniper/contrail-docs/tree/master/doc/release-notes
CC: README | Randy |  |  | Engineering after 5.1 release |  | DockerHub item, it is not depricated, it is simply no longer distributed as Contrail docs from 5.1 onwards | https://www.juniper.net/documentation/en_US/contrail5.0/information-products/topic-collections/release-notes/readme-contrail-50.pdf
OC: Eng Wiki | Randy | [5 empty] | https://github.com/Juniper/contrail-controller/wiki
What 302 redirects will we need? | James
Clickable map | James
New TF Datasheet | Robert